## Amrit
Amrit Sarovar ¦ Kurukshetra | [6 empty] | Amrit |  |  | Amrit + [Sustainability]
[10 empty] | Mandatory |  |  |  | Additional
# | Block | Village | Unique Identification Number | Source of Water | Type (Construction / Renovation) | Status (on PDMS Portal) | Step 1 Dewatering | Step 2 Desilting | Step 3 Embankment | Walkway | Plantation | Benches | Solar Lights | Greywater Management / Wetland | Boundary | Cattle Ghats
1 | Babain | NAKHROJPUR (164) | 01HRKKRBBN0164NAKH001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
2 | Babain | MANGOLI RANGRAN (130) | 01HRKKRBBN0130MANG002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
3 | Ismailabad | AJRANA KHURD (276) | 01HRKKRTNS0276AJRA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
4 | Ismailabad | NAISI (323) | 01HRKKRIML0323NAIS001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
5 | Ismailabad | ROHTI (312) | 01HRKKRIML0312ROHT001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
6 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
7 | Ismailabad | SALPANI KALAN (300) | 01HRKKRIML0300SALP002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
8 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
9 | Ladwa | KHERI DABDALAN (64) | 01HRKKRLDW0064KHER002 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
10 | Ladwa | SURA (50) | 01HRKKRLDW0050SURA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
11 | Ladwa | BUDHA (61) | 01HRKKRLDW0061BODH001 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
12 | Ladwa | DHANORA JATTAN (59) | 01HRKKRLDW0059DHAN001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
13 | Ladwa | JAINPUR JATTAN (78) | 01HRKKRLDW0078JAIN002 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
14 | Ladwa | SAMALKHA (63) | 01HRKKRLDW0063SAMB001 | Sewage Water | Renovation | In progress | Completed | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
15 | Ladwa | CHHALAUNDI (67) | 01HRKKRLDW0067CHHA003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
16 | Ladwa | BAPDA (74) | 01HRKKRLDW0074BAPD001 | Sewage Water | Renovation | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
17 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
18 | Pehowa | ARNAICHA | 01HRKKRPHW0014ARNE002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
19 | Pehowa | BAKHLI (11) | 01HRKKRPHW0011BAKH003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
20 | Pehowa | BIBIPUR KALAN (50) | 01HRKKRPHW0050BIBI002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
21 | Pehowa | RATTANGARH KAKRALI (8) | 01HRKKRPHW0008RATT001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
22 | Pipli | JIRBARI (371) | 01HRKKRPPL0371JIRB001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
23 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
24 | Pipli | SAMANI (29) | 01HRKKRPPL0029SAMA002 | Sewage Water | Renovation | Completed | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
25 | Pipli | SANWLA | 01HRKKRPPL0SANW002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
26 | Pipli | DHIRPUR (408) | 01HRKKRTNS0408DHIR001 | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
27 | Pipli | GOBIND MAJRA (407) | 01HRKKRPPL0407GOVB001 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
28 | Pipli | SIRSLA (397) | 01HRKKRTNS0397SIRS002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
29 | Pipli | SHADIPUR LADWA(367) | 01HRKKRPPL0367SHAD002 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
30 | Pipli | KANIPLA (104) | 01HRKKRPPL0104KANI002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
31 | Pipli | KHAIRA (345) | 01HRKKRPPL0345KHAI001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
32 | Pipli | SODHI (369) | 01HRKKRPPL0369SODH002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
33 | Pipli | MASANA (96) | 01HRKKRPPL0096MASA001 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
34 | Pipli | BIR MATHANA (363) | 01HRKKRPPL003630BIR002 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
35 | Shahabad | TEORA (243) | 01HRKKRSHB0243TEOR001 | Sewage Water | Renovation | In progress | Completed | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
36 | Shahabad | TEORA (243) | 01HRKKRSHB0243TYOR003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
37 | Shahabad | DHANTAURI (97) | 01HRKKRSHB0097DHAN001 | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
38 | Thanesar | DAYALPUR (PART) (383) | 01HRKKRTNS0383DIYA001 | Canal/Borewell | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
39 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
40 | Thanesar | AMIN (33) | 01HRKKRTNS0033AMIN002 | Sewage Water | Renovation | In progress | In progress | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
41 | Thanesar | DAYALPUR (PART)(383) | 01HRKKRTNS0DAYA004 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
42 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM002 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
43 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
44 | Thanesar | BHAINSI MAJGRA | 01HRKKRTNS0018BHAN001 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
45 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM006 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
46 | Thanesar | KHIZARPURA (28) | 01HRKKRTNS0028KHIJ002 | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
47 | Thanesar | DHURALA (404) | 01HRKKRTNS0404DHUR002 | Sewage Water | Renovation | In progress | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
48 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM005 | Sewage Water | Renovation | In progress | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
49 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM009 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
50 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM003 | Sewage Water | Renovation | Completed | Completed | Completed | Completed | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
51 | Thanesar | KIRMACH (6) | 01HRKKRTNS0006KIRM004 | Sewage Water | Renovation | In progress | Completed | In progress | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled
52 | Thanesar | AJRANA KALAN (POND 5) | 01HRKKRTNS0274AJRA004 | Sewage Water | Renovation | Not started | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled | Scheduled

## Dashboard
Status (on PDMS Portal) | COUNTA of Status (on PDMS Portal) | COUNTA of Block | Status (on PDMS Portal) |  |  |  | 30.05.2023
Completed | 25 | Block | Completed | In progress | Not started | Grand Total | Block | Completed | In progress | Not started | Grand Total
In progress | 17 | Babain | 1 |  | 1 | 2 | Babain | 1 |  | 1 | 2 | 1
Not started | 10 | Ismailabad | 4 | 1 |  | 5 | Ismailabad | 4 | 1 |  | 5 | 5
Grand Total | 52 | Ladwa | 3 | 5 | 1 | 9 | Ladwa | 3 | 5 | 1 | 9 | 8
|  | Pehowa | 5 |  |  | 5 | Pehowa | 5 |  |  | 5 | 5
|  | Pipli | 4 | 4 | 5 | 13 | Pipli | 3 | 5 | 5 | 13 | 8
|  | Shahabad | 1 | 2 |  | 3 | Shahabad | 1 | 2 |  | 3 | 3
|  | Thanesar | 7 | 5 | 3 | 15 | Thanesar | 7 | 5 | 3 | 15 | 12
|  | Grand Total | 25 | 17 | 10 | 52 | Grand Total | 24 | 18 | 10 | 52 | 42